## Q3 Calendar
Xeno Marketing — Q3 2026 Calendar (Jul–Sep) ¦ Target: 10 SQLs
Week | Phase | Events (Top 50) | ABM + Game (Top 50/200) | Inbound + Case Studies | Research + Webinar | Founder LinkedIn | Always-on / Ops
Jul W1 | Activate | Lock event format + city | Finalise + enrich Top 50 | Publish case study #1; ROI calculator live | Scope retail research | POV post #1 | Dashboard live; tracking ON
Jul W2 | Activate | Build invite list | ABM wave 1 -> Top 50 | Gated case study push | Field research survey | POV post #2 | List clean-up / suppression
Jul W3 | Activate | - | Game campaign #1 | Inbound nurture | - | Customer story repost | Enrich Next 200
Jul W4 | Activate | Confirm speakers | ABM wave 1 review | Case study #2 | Research data in | POV post #3 | Q2-vs-Q3 ratio check
Aug W1 | Activate + Convert | ROUNDTABLE #1 (Top 50) | ABM -> Next 200 (segmented) | Roundtable follow-up assets | Webinar invites out | Event teaser | Gifting to Next 200
Aug W2 | Activate + Convert | Roundtable follow-up mtgs | Game campaign #2 | Case study #3 | Webinar reminders | POV post #4 | Mid-funnel scoring
Aug W3 | Activate + Convert | - | ABM wave 2 -> Top 50 | Inbound nurture | WEBINAR (live) + research launch | Webinar amplification | Data-standard checkpoint
Aug W4 | Activate + Convert | Plan event #2 (if working) | Webinar -> SQL follow-up | Case study #4 | Webinar replay nurture | POV post #5 | SPEND go/no-go review
Sep W1 | Convert | EVENT #2 (if on track) | Game campaign #3 | Proof assets refresh | Post-webinar sequence | Customer advocacy post | Pipeline review
Sep W2 | Convert | Event follow-up mtgs | ABM -> close gaps | Inbound -> meetings | - | POV post #6 | Mid-quarter ratio + spend review
Sep W3 | Convert | 2nd-priority invites -> Next 200 | Push pipeline -> SQLs | Case-study close support | - | Advocacy post | Attribution clean-up
Sep W4 | Convert | - | Final SQL push | - | Plan Q4 / launch research | Q3 wrap post | Q3 RESULTS vs 10; hand-off to launch
Legend:
Jul = Activate | Aug = Activate + Convert | Sep = Convert
Red bold = key milestone (event/webinar/review/results)
Note: columns = 5 candidate activities; keep the 3 chosen after the pitch, drop the rest.